## Slide 1
KAGADI DISTRCT
MICROSCALE IRRIGATION PROGRAM IMPLEMENTATION STATUS AS OF
8TH FEBRUARY 2024

## Slide 2
Introduction
Kagadi District is among the phase two UgIFT Micro-scale implementing Districts within Cluster 6, promoting the use and adoption of Micro-scale irrigation kits to provide water for production. The Project is being implemented in 35 Lower Local Governments that is 09 Town Councils and 26 Sub-Counties that form Kagadi District. Project implementation started in July 2022 Financial Year 2022/2023.

## Slide 3: Activities that were implemented F/Y 2022/2023
Awareness raising across the District
1,175 Expression of interests were recorded across the District
484 Farm visits prepared
257 Farm visits successfully conducted
21 Farmers have already committed the one million shillings
7 Field demonstration equipment set

## Slide 4
S/N | LLG | NO. OF EOI | NO. OF FARM VISITS
1 | Buhumuliro | 58 | 0
2 | Burora | 16 | 2
3 | Bwikara | 78 | 38
4 | Isunga | 50 | 11
5 | Galiboleka | 49 | 5
6 | Kabamba | 30 | 6
7 | Kagadi | 23 | 2
8 | Kamuroza | 13 | 5
9 | Kicucura | 39 | 6
10 | Kiryanga | 40 | 4
11 | Kagadi Town council | 72 | 6
12 | Kanyabebe | 16 | 0

## Slide 5
S/N | LLG | NO. OF EOI | NO. OF FARM VISITS
13 | Kinyarugonjo | 22 | 6
14 | Kyakabadiima | 12 | 1
15 | Kyanaisoke | 33 | 12
16 | Kyaterekera | 16 | 4
17 | Kyaterekera Town Council | 55 | 7
18 | Kyenzige | 24 | 7
19 | Kyenzige Town Council | 19 | 3
20 | Mabaale | 73 | 23
21 | Mairirwe | 38 | 7
22 | Mpeefu | 21 | 5
23 | Mpeefu Ya Sande | 8 | 0
24 | Muhorro | 18 | 1

## Slide 6
S/N | LLG | NO. OF EOI | NO. OF FARM VISITS
25 | Muhorro Town Council | 48 | 17
26 | Ndaiga | 54 | 0
27 | Nyabutanzi | 27 | 25
28 | Nyakarongo | 69 | 4
29 | Paacwa | 42 | 8
30 | Rugashali | 52 | 4
31 | Ruteete | 60 | 6
 | TOTAL | 1,175 | 257

## Slide 7: FAMERS WHO HAVE ALREADY COMMITTED 1,000,000 AND PASSED BY DTPC AS AREQUIREMENT
S/N | NAMES | LLG
1 | Sazi Robert | Kyanaisoke
2 | Buhenzire Evalyne | Bwikara
3 | Kasumba Yusufu | Muhorro T/C
4 | Birungi Julius | Muhorro T/C
5 | Munyahwera Gard | Nyakarongo
6 | Madiina Biingi | Mabaale T/C
7 | Ssetabi Andrea | Mabaale T/C

## Slide 8: FAMERS WHO HAVE ALREADY COMMITTED 1,000,000 AND PASSED BY DTPC AS AREQUIREMENT
S/N | NAMES | LLG
8 | Rubanga Charles | Mabaale T/C
9 | Rwebembera William | Kicucura
10 | Tiberindwa Gard | Ruteete T/C
11 | Twinamatsiko Saul | Ruteete T/C
12 | Aligonzawenka Vincent | Kyanaisoke
13 | Irumba Vincent | Paacwa T/C
14 | Mulumba Ali | Muhorro T/C

## Slide 9: FAMERS WHO HAVE ALREADY COMMITTED 1,000,000 AND PASSED BY DTPC AS AREQUIREMENT
S/N | NAMES | LLG
15 | Bazitya Raphael | Kyanaisoke
16 | Kasungwa Kisembo M | Nyabutanzi

## Slide 10: CHALLENGES IN IMPLEMENTATION
Loss of interest by the farmers after expression of interest
High costs involved in co-payment
Understaffing in LLGs
Lack of access to water sources
Systems failure
Low turn up for meetings by farmers
Delays caused by release of funds

## Slide 11: I THANK YOU FOR LISTENING